## Sheet1
Excel Spreadsheet Cross Check
Project Summary Costs
|  | Labor Total (Approximate) |  | 24736.1405
|  | Furniture and Equipment |  | 97899.9999
|  | Project Total (Approx) |  | 122636.1404
Labor Costs
Hourly Rate
|  | Fidel Rivera |  | 70
|  | Mimi Vespa |  | 57.5
|  | Hannah Thomas |  | 54
|  | Robert Tutone |  | 48.75
|  | John Fontaine |  | 46.5
|  | Dan Shannon |  | 45.5
|  |  | Average: | 53.7083
Equipment and Furniture Costs
|  |  |  | Quantity | Cost (each) | Total
| Laptops with software suite |  |  | 14 | 2375 | 33250
| VoIP Handsets |  |  | 14 | 650 | 9100
| Cubicle Furniture |  |  | 14 | 2750 | 38500
| Xerox High Speed Copier/Printer |  |  | 1 | 6350 | 6350
| Ciso Aironet Wireless Access Points |  |  | 6 | 875 | 5250
| Ciena ME4300 Aggregation Switch |  |  | 1 | 4825 | 4825
| Cat 6E Network Cabling |  |  | 7 | 89.2857 | 624.9999
|  |  | Equipment and Furniture Total: |  |  | 97899.9999
Project Requirements/Tasks | [7 empty] | Time(hrs) | Hourly Rate | Approx. Cost
Initiating
| Develop Project Charter | [6 empty] | 10 | 53.71 | 537.1
| Meet with Procurement Department | [6 empty] | 3 | 53.71 | 161.13
Kick-Off Meeting
|  | Conference Room Meeting | [5 empty] | 1 | 53.71 | 53.71
|  | Warehouse Site Survey | [5 empty] | 0.14 | 53.71 | 7.5194
|  | Determine preffered furniture supplier | [5 empty] | 3.01 | 53.71 | 161.6671
Planning
Design and Specify Material
|  | Select Cucible Make and model and floor layout diagram | [5 empty] | 1 | 53.71 | 53.71
|  | Ensure furniture is of the same make model and color as existing furniture | [5 empty] | 2 | 53.71 | 107.42
|  | Determine Laptops and Software to be ordered | [5 empty] | 4 | 53.71 | 214.84
|  | Specify VoIP Phones to be ordered | [5 empty] | 2 | 53.71 | 107.42
|  | Determine which model of VOIP headsets will be ordered | [5 empty] | 2 | 53.71 | 107.42
|  | Meet and determine make and model of printer | [5 empty] | 1 | 53.71 | 53.71
|  | Meet with team to determine exact model of 6e Cable to be ordered | [5 empty] | 1 | 53.71 | 53.71
|  | Determine hardware for new wireless access points | [5 empty] | 8 | 53.71 | 429.68
Procurment
|  | Order Cubicle Furniture | [5 empty] | 4 | 53.71 | 214.84
|  | Order Laptops with Software | [5 empty] | 8 | 53.71 | 429.68
|  | Order VoIP Phones | [5 empty] | 8 | 53.71 | 429.68
|  | Order Printer | [5 empty] | 8 | 53.71 | 429.68
|  | Order 7 CAT 6e cables | [5 empty] | 8 | 53.71 | 429.68
|  | Order Ciso ME3400 aggregation switch | [5 empty] | 8 | 53.71 | 429.68
|  | Order hardware for six new wireless access points | [5 empty] | 16 | 53.71 | 859.36
Executing
Receive and Inspect Material
|  | R&I Cubicle Furniture | [5 empty] | 16 | 53.71 | 859.36
|  | R&I Laptop with Software | [5 empty] | 8 | 53.71 | 429.68
|  | R&I VoIP Phones | [5 empty] | 8 | 53.71 | 429.68
|  | R&I Printer | [5 empty] | 8 | 53.71 | 429.68
|  | R&I 7 CAT 6e cables | [5 empty] | 8 | 53.71 | 429.68
|  | R&I Ciso ME3400 aggregation switch | [5 empty] | 8 | 53.71 | 429.68
|  | R&I hardware for six new wireless access points | [5 empty] | 8 | 53.71 | 429.68
Installation
|  | Install cubicle furnitre | [5 empty] | 16 | 53.71 | 859.36
|  | Install Laptops with Software | [5 empty] | 8 | 53.71 | 429.68
|  | Install VoIP Phones | [5 empty] | 13.2 | 53.71 | 708.972
|  | Install Printer | [5 empty] | 13.2 | 53.71 | 708.972
|  | Install ME3400 Aggregation switch | [5 empty] | 16 | 53.71 | 859.36
|  | Install 1 CAT 6e cable from new workstation to old warehouse | [5 empty] | 16 | 53.71 | 859.36
|  | Install hardware for six new wireless access points | [5 empty] | 16 | 53.71 | 859.36
|  | Install 6 CAT 6e cables from each acces point to the aggregation switch | [5 empty] | 16 | 53.71 | 859.36
|  | Install licenses for Windows Enterprise OS on each computer | [5 empty] | 16 | 53.71 | 859.36
|  | Install licenses for Microsot Office on each computer | [5 empty] | 16 | 53.71 | 859.36
Closing
Closing meetings
|  | Meet with IT Department and all divisions about what data needs to remain on cloud storage + new laptops | [5 empty] | 4 | 53.71 | 214.84
|  | Meet with cloud services company to ensure that data sync will be smooth and compatible | [5 empty] | 4 | 53.71 | 214.84
|  | Meet with IT Specialists to ensure that wireless access points will use WPA2 encryption format | [5 empty] | 4 | 53.71 | 214.84
Testing and Troubleshooting
|  | Test and troubleshoot existing multimode fiber to ensure usability | [5 empty] | 16 | 53.71 | 859.36
|  | Test and troubleshoot main router | [5 empty] | 16 | 53.71 | 859.36
|  | Test and troubleshoot 6e cable | [5 empty] | 16 | 53.71 | 859.36
|  | Test and troubleshoot aggregation switch | [5 empty] | 16 | 53.71 | 859.36
Connecting
|  | Connect printer to network | [5 empty] | 16 | 53.71 | 859.36
|  | Connect aggregation switch to main server room's main router (Cisco 7606's) | [5 empty] | 16 | 53.71 | 859.36
|  | Connect laptops to existing cloud storage system | [5 empty] | 20 | 53.71 | 1074.2
|  | Connect all phones and headsets to the existing VoIP pbx phone system | [5 empty] | 16 | 53.71 | 859.36
|  | Adjust printer to allow shared printing with all PC's | [5 empty] | 8 | 53.71 | 429.68
[7 empty] | LABOR TOTALS: | 460.55 | 36.5 | 24736.1405